## sessions
date | start | end | activity | worker | elapsed (hours)
2016-05-31 | 17:23 | 17:56 | write out aims/steps | Nicholas & Cesar | 0.5
2016-05-31 | 18:01 | 18:12 | create a test .csv file used for main page user posts | Nicholas | 0.2
2016-05-31 | 19:25 | 19:44 | create a simple function to append to the mainpage csv file | Cesar | 0.3
2016-05-31 | 21:18 | 21:47 | create a post HTML template, and the Python code that prints out the template with data | Nicholas | 0.5
2016-06-01 | 16:21 | 16:49 | create python module for logging in to existing account | Cesar | 0.5
2016-06-01 | 16:52 | 17:01 | create python code for creating a new account & appending to profiles csv | Cesar | 0.2
2016-06-01 | 17:54 | 18:13 | began work on module that checks user's logged in/out state | Cesar | 0.3
2016-06-01 | 21:53 | 22:29 | create code that takes multiple posts from CSV and prints multiple HTML tables | Nicholas | 0.6
2016-06-02 | 17:22 | 18:08 | create main.py, that detects user's input and calls other modules accordingly; works with login & register so far | Cesar | 0.8
2016-06-02 | 19:39 | 20:31 | work on post comments; mainly the comment html and experimenting with CSS | Nicholas | 0.9
2016-06-03 | 17:02 | 18:23 | work on mainpage HTML and CSS; changed post tables to accomadate CSS | Cesar & Nicholas | 1.4
2016-06-03 | 18:54 | 19:08 | work on python code to generate post comment section | Cesar | 0.2
2016-06-03 | 20:31 | 21:07 | work on HTML form for making new comment | Nicholas | 0.6
2016-06-04 | 10:49 | 12:33 | work on python code for posting new comment | Cesar | 1.7
2016-06-07 | 22:38 | 23:05 | work on HTML form for making new post | Nicholas | 0.4
2016-06-08 | 16:58 | 17:34 | work on python code for creating new post & appending to mainpage.csv | Cesar | 0.6
2016-06-08 | 17:36 | 18:34 | organizing & fixing up spaghetti code | Cesar | 1.0
2016-06-08 | 20:21 | 21:01 | add new login HTML page | Nicholas | 0.7
2016-06-08 | 22:19 | 22:32 | added redirects and error pages | Cesar | 0.2
2016-06-10 | 17:53 | 18:33 | work on profile page HTML template | Nicholas | 0.7
2016-06-10 | 19:37 | 20:50 | make every user input conform to the csv files | Cesar | 1.2
2016-06-10 | 22:22 | 23:28 | work on python code for generating personal profile pages and editing about me's | Nicholas | 1.1
2016-06-11 | 8:35 | 8:56 | finished personal profile pages and editing about me's | Cesar | 0.4
2016-06-11 | 9:34 | 10:12 | work on python/HTML code for viewing other users' profiles | Cesar | 0.6
2016-06-11 | 10:13 | 10:50 | work on python/HTML code for liking/unliking posts | Cesar | 0.6
2016-06-11 | 15:52 | 17:00 | work on python/HTML code for editing account settings (owner, password) | Nicholas | 1.1